## Timeline
ALLIED
[15 empty] | 2023 | [11 empty] | 2024
[7 empty] | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
WBS | Activities | Priority | Budget | Start | Finish | Duration in months | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
1 | Supports WG | NORMAL | 111667 | 2022-03-22 | 2024-04-01 | 24.3616
1.6 | Activity 1: Kick-off building brdiges online meeting | NORMAL |  | 2023-05-01 | 2023-07-01 | 2.0055 | bar: 2023 May 17 to 2023 Jul 19
1.1 | Activity 2. Develop emergency and non-emergency resources | NORMAL |  | 2022-04-15 | 2023-03-24 | 11.2767 | bar: May 5 to 2023 Mar 15
1.1.1 | Develop emergency and non-emergency resource for 2 West African Countries | NORMAL |  | 2022-04-15 | 2023-03-24 | 11.2767 | bar: May 5 to 2023 Mar 15
1.1.2 | Develop emergency and non-emergency resource for Guatemala and Brazil? | NORMAL |  | 2022-04-15 | 2023-03-24 | 11.2767 | bar: May 5 to 2023 Mar 15
1.1.3 | Monitor impact of The Phonebook in Colombia, Mexico and Kenya | NORMAL |  | 2022-05-01 | 2022-07-01 | 2.0055 | bar: May 5 to Jul 7
1.1.4 | Disseminate the Phonebook Philippines | NORMAL |  | 2022-05-01 | 2022-07-01 | 2.0055 | bar: May 5 to Jul 7
1.2 | Activity 3. Hold building bridges workshops | NORMAL |  | 2023-04-01 | 2023-11-01 | 7.0356 | bar: 2023 Apr 16 to 2024 Mar 27
1.2.1 | Brazil | NORMAL |  | 2023-04-01 | 2023-05-01 | 0.9863 | bar: 2023 Apr 16 to 2023 May 17
1.2.2 | Colombia | NORMAL |  | 2023-06-01 | 2023-07-01 | 0.9863 | bar: 2023 Jun 18 to 2023 Jul 19
1.2.3 | Guatemala | NORMAL |  | 2023-08-01 | 2023-09-01 | 1.0192 | bar: 2023 Aug 20 to 2023 Sep 21
1.2.4 | Kenya - with time see if expand | NORMAL |  | 2023-10-01 | 2023-11-01 | 1.0192 | bar: 2023 Jun 18 to 2023 Jul 19; 2023 Oct 22 to 2023 Nov 23
1.2.5 | Mexico | NORMAL |  | 2023-06-01 | 2023-07-01 | 0.9863
1.2.6 | Philippines | NORMAL |  | 2023-04-01 | 2023-05-01 | 0.9863 | bar: 2024 Feb 26 to 2024 Mar 27
1.3 | Activity 4. Support the development of networks of defenders and support organizations in priority countries | NORMAL |  | 2023-06-01 | 2024-04-01 | 10.0274 | bar: 2023 Jun 18 to 2024 Mar 27
1.4 | Activity 5. Revise, lay out and publish the guidance developed by ALLIED to support networks to address emergency response. | NORMAL |  | 2022-08-15 | 2022-10-15 | 2.0055 | bar: Aug 8 to Oct 10
1.6 | Activity 6: Hold a defender network exchange online or hybrid to share experiences, lessons learned: thematic? | NORMAL |  | 2023-05-01 | 2023-07-01 | 2.0055 | bar: 2023 May 17 to 2023 Jul 19
1.8 | Activity 7: Organize a roundtable with funders to launch report on LED needs. | NORMAL |  | 2022-04-01 | 2022-05-15 | 1.4466 | bar: May 5
1.5 | Activity 8. Create a campaign for engagement of climate activists with defenders information and reach out to climate networks to provide information that is relevant to them. | NORMAL |  | 2022-06-01 | 2022-09-01 | 3.0247 | bar: Jun 6 to Sep 9
1.7 | Activity 9: Identify training resources needed by defenders and upload to environment-rights.org website | NORMAL |  | 2022-03-22 | 2024-04-01 | 24.3616
1.9 | Activity 10: Support Alliance members that seek to train their networks to access support resources, build skills in personal and digital protection. | NORMAL |  | 2022-03-22 | 2024-04-01 | 24.3616
International Coordinator
Support the work of working groups
2 | Support monthly LAWG learning sessions | NORMAL |  | Ongoing |  | na
2.1 | Support monthly DWG meetings | NORMAL |  | Ongoing |  | na
2.2 | Communications and engagement | NORMAL
| Recruit communications officer |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Develop ALLIED website |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Create and share shared calendar |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Develop document management system |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Launch internal newsletter |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Send monthly newsletter |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Create templates and institutional emails |  |  | 2022-05-01 | 2022-05-31 | 0.9863 | bar: May 5
| Reach out to memebers to identify opportunities for collaboration |  |  | 2022-06-01 | 2022-08-01 | 2.0055 | bar: Jun 6 to Aug 8
| Reach out to other coallitions to explore overlaps |  |  | 2022-06-01 | 2022-08-01 | 2.0055 | bar: Jun 6 to Aug 8
| Work to develop a rapid response strategy |  |  | 2022-06-01 | 2022-08-01 | 2.0055 | bar: Jun 6 to Aug 8

## Budget SWG
111667 | TOTAL | Activity 1: Kick-off defender network exchange online to identify areas of concern | Activity 2. Deverlop emergency and non-emergency resources | Develop emergency and non-emergency resource for 2 West African Countries | Develop emergency and non-emergency resource for Guatemala | Monitor impact of The Phonebook in Colombia | Monitor impact of The Phonebook in Mexico | Monitor impact of The Phonebook in Kenya | Disseminate the Phonebook Philippines | Activity 3. Hold building bridges workshops | Brazil | Colombia | Guatemala | Kenya | Mexico | Philippines | Activity 4. Support the development of networks of defenders and support organizations in priority countries | Activity 5. Revise, lay out and publish the guidance developed by ALLIED to support networks to address emergency response. | Activity 6: Hold a defender network exchange online to share experiences, lessons learned. | Activity 7: Organize a roundtable with funders to launch report on LED needs. | URG |  | Activity 8: Identify training resources needed by defenders and upload to environment-rights.org website
DIRECT COSTS | [22 empty] | Activity 9. Create a campaign for engagement of climate activists with defenders information and reach out to climate networks to provide information that is relevant to them.
a) Personnel | [22 empty] | Activity 10: Support Alliance members that seek to train their networks to access support resources, build skills in personal and digital protection.
Total Personnel | 48040 | 2040 | 16000 | 4000 | 4000 | 2000 | 2000 | 2000 | 2000 | 12000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 13000 | 2000 | 3000 |  | 11040 | 11040
b) Other Direct Costs | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Seminars/Workshops | [20 empty] | 0
Room rental (X seminars x X days) | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Interpretation services (X seminars x X days) | 16000 | 2000 | 0 | [6 empty] | 12000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  |  |  | 2000 | 6000
Travel + accomodation | 33000 |  | 0 | [6 empty] | 33000 | 5500 | 5500 | 5500 | 5500 | 5500 | 5500 |  |  |  |  | 5500
Meals/refreshments (X participants x X days) | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Zoom | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Materials | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Website | [20 empty] | 0
Website design and development | 3000 |  | 3000 | 1500 | 1500 |  |  |  |  | 0 | [10 empty] | 0
Security for website | 0 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Website maintenance | 2000 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Server and hosting | 192 |  | 0 | [6 empty] | 0 | [10 empty] | 0
Project Activities | [20 empty] | 0
Design of report and related materials | 3300 |  | 900 | [5 empty] | 900 | 0 | [7 empty] | 2400 |  |  | 2400
Printing and distribution of manual | 2000 |  | 2000 | [5 empty] | 2000 | 0 | [10 empty] | 0
Total Other Direct Costs | 59492 | 2000 | 5900 | 1500 | 1500 | 0 | 0 | 0 | 2900 | 45000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 0 | 2400 | 0 | 2000
TOTAL | 107532 | 4040 | 21900 | 5500 | 5500 | 2000 | 2000 | 2000 | 4900 | 57000 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500 | 13000 | 4400 | 3000 | 2000 | 24940
Bank fees | 3469.08 | [19 empty] | 560
Unforseen | 665.92
25500

## URG
| IC |  |  | 162500 | SSWG |  | 25500
| Amount | COP | Units | IC Total
Salaries |  |  |  | 81535 |  |  | 11040
Mariana | 2975 |  | 23 | 68425 | 250 | 23 | 5750
URG LAC | 570 |  | 23 | 13110 | 230 | 23 | 5290
Fringe Benefits
Supplies & Materials
Contractual Services |  |  |  | 22604.0333 |  |  | 6000
Fellow Africa | 750 |  | 23 | 17250 |  |  | 0
Interpreters |  |  |  |  | 6000 | 1 | 6000
Accountant | 138.8889 |  | 24 | 3333.3333 |  |  | 0
Website design and development (Alex IT) | 2020.7 |  | 1 | 2020.7 |  |  | 0 | 2020.7
Communication Costs |  |  |  | 2578.38 |  |  | 2400
Design and comms | 600 |  | 4 | 2400 | 600 | 4 | 2400
Zoom | 178.38 | 690745 | 1 | 178.38 |  |  |  | 178.38
Travel & Per Diem |  |  |  | 0 | 5500 | 1 | 5500
Occupancy | 240 |  | 24 | 5760 |  |  | 0 | 5760
Other Costs |  |  |  | 38192.4791 |  |  | 0
Domain, server and hosting | 192.4791 | 723529 | 1 | 192.4791 |  |  | 0 | 192.4791
Trust | 38000 |  | 1 | 38000 |  |  |  | 38000
Total Direct Costs |  |  |  | 150669.8925 |  |  | 24940
Indirect Costs
Bank Fees |  |  |  | 677.0145 |  |  | 99.76 | 0
Taxes |  |  |  | 11153.275 |  |  | 460 | 0
Gen & Admin. Expenses
Total Indirect Costs |  |  |  | 11830.2895 |  |  | 559.76
Total Project Costs |  |  |  | 162500.182 |  |  | 25499.76
124500.182

## TOTAL
| IC |  |  | 163000 | SSWG |  | 111667
| Amount | COP | Units | IC Total | Amount | Units | Total | TOTAL
Salaries |  |  |  | 82457.3 |  |  | 50791 | 133248.3
Mariana | 2980 |  | 23 | 68540 | 295 | 23 | 6785 |  | 24232.5607 | 3275 | 11790000 | 64476 | 4549 | 16376400
Community engagement | 605.1 |  | 23 | 13917.3 | 300 | 23 | 6900 |  |  | 905.1 | 3348870 | 50791
Subgrants |  |  |  |  | 37106 | 1 | 37106
Fringe Benefits
Supplies & Materials
Contractual Services |  |  |  | 22604.0333 |  |  | 14800 | 37404.0333
Fellow Africa | 750 |  | 23 | 17250 |  |  | 0 |  |  |  | Por evento
Interpreters URG |  |  |  |  | 4800 | 1 | 4800 |  |  | 17280000 | 2480000 | 6.9677
Interpreters Subgrants |  |  |  |  | 10000 | 1 | 10000
Accountant | 138.8889 |  | 24 | 3333.3333 |  |  | 0
Website design and development (Alex IT) | 2020.7 |  | 1 | 2020.7 |  |  | 0
Communication Costs |  |  |  | 1778.38 |  |  | 9100 | 10878.38
Design and comms | 400 |  | 4 | 1600 | 200 | 4 | 800 |  | 133.3333
Website development and maintainance |  |  |  |  | 5000 | 1 | 5000
Desing and comms subgrants |  |  |  |  | 3300 | 1 | 3300
Zoom | 178.38 | 690745 | 1 | 178.38 |  |  | 0
Travel & Per Diem |  |  |  | 0 |  |  | 35000 | 35000
URG travel |  |  |  |  | 6000 | 1 | 6000
Subgrants travel |  |  |  |  | 29000 | 1 | 29000
Occupancy | 240 |  | 23 | 5520 |  |  | 0 | 5520
Other Costs |  |  |  | 38192.4791 |  |  | 0 | 38192.4791
Domain, server and hosting | 192.4791 | 723529 | 1 | 192.4791 |  |  | 0
Trust | 38000 |  | 1 | 38000
Total Direct Costs |  |  |  | 150552.1925 |  |  | 109691 | 260243.1925
Indirect Costs
Bank Fees |  |  |  | 676.4849 |  |  | 438.764
Taxes |  |  |  | 10966.4 |  |  | 1085.6
Gen & Admin. Expenses
Total Indirect Costs |  |  |  | 11642.8849 |  |  | 1524.364 | 13167.2489
Total Project Costs |  |  |  | 162195.0773 |  |  | 111215.364 | 273410.4413
Balance |  |  |  | 804.9227 |  |  | 451.636 | 1256.5587