## Sheet1
| Outputs | Deadline | Lead partner | Deliverable | Supporting partners | Notes
East Africa criminalization | 1. Contribute to fair reporting on criminalization of ILEDs |  |  |  |  | • Support the coordination of partners to project meetings • Identification of partners in Tanzania and Uganda • Define an advocacy approach to decrease criminalization in each country • A budget for an assessment of criminalization cases similar to what was done in Kenya for Tanzania and Uganda and subgrants to these partners to do the work – We should find out how much ELAW gave to Katiba to do the original assessment. Review ALLIED and check for overlaps – see if similar for all three countries or not. • Support for helping them getting three briefs: one for each country, done for each country and sending to appropriate agencies – Ministry Human Rights / Justice as part of advocacy strategy etc. • Internal ALLIED learning event to show what was learnt in project and or an external one. External event. Tanzania Budget.
| Hold two online workshops with participation from Kenya, Uganda and Tanzania with environmental reporters and criminal reporters on the use of laws to criminalize defenders. | Oct-Nov 2022 | Katiba | Informal notes/summary report | Parters no help identify best partners in Uganda and Tanzania
2. Contribute to increased support for ILEDs in cases of criminalization
| Organize one in person training on criminalization for Lawyers who are connected to the Defend Defenders Coalition, Natural Justice and Law Society of Kenya fund to support defenders. | TBC - Emily. Early 2023 | Katiba | Informal notes/summary report | Natural Justice, Defend Defenders Coalition and Law Society to help identify and reach out to lawyers. Funding/extra support to make sure we are able to have East Africa reach CJGEA share existing support tools and resources with participants
3. Ensure defenders have more knowledge and awareness and help provide education for how to get in touch with and get support from lawyers/fund
| Develop a security plan/risk analysis for 1-2 Criminalized defenders. | August 2022-Jan 2023 | CJGEA | "Template" for future cases | URG help coordinate action with OB and Kamara. CSOs - PI, FL
| Hold workshop with ILEDs in Kenya, inviting at least one from Uganda and one from Tanzania Explicitly add a session during the workshop on ‘learning on criminalization good practices and response mechanisms’ within the annual CJGEA Workshop for Land and Environmental Defenders. Invite at least one defender from Tanzania and one from Uganda, to join the workshop in person, and consider opening spaces for the remote participation of other defenders from these countries. During the workshop, also share support resources, website and app. | June 2022. | CGJEA | Event report | Katiba: help organize the criminalization session and reach out and engage defenders and networks in Uganda and Tanzania Explore whether and how RRI can contribute to this workshop. URG to coordinate meeting. URG contribute to embedding topics on support resources and tools in the workshop agenda.
| Hold meetings to engage with defenders and defender networks in Uganda and Tanzania Hold two virtual meetings with defenders ILEDs and defender networks in Uganda and Tanzania and prepare a report to share lessons learned in these two countries. | December 2022 -April 2023 | CJGEA | Informal notes/summary report | Katiba: reach out and engage defenders and networks in Uganda and Tanzania and provide input to the report. RRI and law and advocacy working group to support advocacy and dissemination strategy. URG to help coordinate action. Dissemination and advocacy and be done jointly with Katiba’s policy statement strategy (see below).
4. Contribute to stronger frameworks
| Produce one 1-2 pages policy statements on use of laws in Kenya, Uganda, and Tanzania to criminalize ILEDs. Share the resulting policy statement with NHRIs and other relevant actors including in the Judiciary. | TBC - RRI | Katiba |  | URG to help Katiba identify experts in Uganda and Tanzania who can give input on the laws and the use of criminalization laws in Uganda and Tanzania. Coordinate with the Defend Defenders Coalition and with RRI to see if they can contribute and how. WRI, RRI and the law and advocacy WG to support advocacy and dissemination strategy. URG to help coordinate action between all partners. Can be done jointly with CJGEA’s report on criminalization in Uganda and Tanzania – see above.